## Slide 1: IsoBank Depositors Testing Kick-Off
Chris Jordan
TACC Data Management and Collections Group
July 2020

## Slide 2: Outline
Brief Status Intro
Process and Timeline
David Walling - Tech discussion and demo
Q & A

## Slide 3: Tech implementation Status
Some schedule and process changes from the plan as described at the Madison Workshop
Significant changes leading to delays:
  Material Type hierarchy changed to a new model with different “root” (geosphere, hydrosphere, etc)
  Some major re-implementation of metadata handling in the site and database
  “Events, dear boy, events”

## Slide 4: Upsides
Consensus that the new material type much better at accommodating all IsoBank-related disciplines (thanks to Gabe Bowen and Environmental Systems committee)
First implementation will be a single-step process for uploading all data at once (as opposed to the two-step Lab + Researcher model shown in Madison)
New metadata model much easier to manage, supports changes and expansion
  Includes ability to document metadata alongside definition in-interface
Overall much better able to accommodate ongoing revisions to metadata requirements and variations amongst disciplines

## Slide 5: Process from here
Today – will describe/show the ingest process, what will be needed from you and what’s still in development
This week – dissemination of metadata templates for use in adjusting current data for IsoBank ingest
Two weeks following dissemination, we ask that you complete the deposit spreadsheets and return them to us
As we receive returned spreadsheets, we will run through the ingest process, find bugs and problems, and work individually with depositor to resolve issues

## Slide 6: Next major milestone
Roughly one month from today, we will meet again
Should have found and resolved any major issues with the template ingest
With sufficient progress on the material type hierarchy, should be able to release a template generator
These two goals should allow us to release the deposit tools to more direct interaction

## Slide 7: Considerations and Feedback requests
Interested generally in how easy it is to get existing data “marked up” to the IsoBank metadata formats and requirements
Documentation of metadata fields and options will be provided in a document distributed/linked to along with template spreadsheets
The number of ”Required” fields is quite large – an issue to be worked out in the next couple of months is how much of what is required is consistently available
No data from this process will be made public